## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Laying Distribution System for SASAN and its adjoining Mouza Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000748/2021-2022 | 487/RD/PHE | 25/02/2022 | 27/03/2022 | BHOLA PAUL | 85.26 | 80.75 | 94.7 | 75
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | FHTC (Functional Household Tap Connection) for Sasan Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000004/2022-2023 | 1016/RD/PHED | 12/05/2022 | 26/06/2022 | M/S HINDUSTHAN CONSTRUCTION | 43.64 | 29.41 | 67.41 | 20
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SASAN PWSS [Augmentation] and its adjoining Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000080/2022-2023 | 1533/RD/PHE | 25/08/2022 | 24/09/2022 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 0.7 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SHASAN Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000728/2022-2023 | 2274/MLMD | 31/08/2022 | 15/10/2022 | ANIMA ENTERPRISE | 6.1 | 6.08 | 99.64 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SASAN Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000727/2022-2023 | 2273/MLMD | 31/08/2022 | 15/10/2022 | MAA BHABOTARINE ENTERPRISE | 7.54 | 5.87 | 77.85 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000127/2022-2023 | 1519\RD | 24/08/2022 | 31/08/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000131/2022-2023 | 1522\RD | 24/08/2022 | 31/08/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Construction of 2Nos. Tube-Well (250mm diameter x 150mmx150mtr) for Augmentation of SASAN Water Supply Scheme in HEMTABAD Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000047/2022-2023 | 1201/RD/PHE | 06/06/2022 | 06/07/2022 | M/S SARKAR ENTERPRISE | 18.2 | 17.52 | 96.31 | 1
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Over Pile Foundation For Augmentation of Sasan Water W/S Scheme in Hemtabad Block in Uttar Dinajpur District. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000052/2022-2023 | 1239/RD/PHE | 20/06/2022 | 10/07/2022 | K.S. GROUP | 1.99 | 1.92 | 96.87 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 641/RD/PHE | 23/03/2022 | 23/03/2022 | Resource Division | 4.86 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1981/RD/PHE | 09/11/2022 | 09/11/2022 | Resource Division | 9.56 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | xerox bill |  |  | VCH/001768/2022-2023 | BP-2022-23-210 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | xerox bill |  |  | VCH/001766/2022-2023 | BP-2022-23-208 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum)of SASAN Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000208/2022-2023 | 77/RD/PHE | 17/01/2023 | 07/12/2024 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 84.28 | 37.6 | 44.61 | 95
15 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Sasan Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000270/2022-2023 | 434/RD/PHE | 10/02/2023 | 27/03/2023 | SHYAM ENTERPRISE SHYAMENTERPRISE.RNJ@GMAIL.COM | 3 | 2.41 | 80.28 | 100
16 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. |  |  | BILL/00216/2023-2024 |  | 15/06/2023 | 15/06/2023 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. |  |  | BILL/00362/2023-2024 | BP-2023-24-75 | 19/07/2023 | 19/07/2023 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Laying of Additional Pipe Line at SASAN Piped Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, P.H.E. Dte.(Augmentation of Sasan PWSS) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000042/2024-2025 | 1702/RD/PHE | 10/06/2024 | 10/07/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 8.38 | 0 | 0 | 100
19 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sasan PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000486/2024-2025 | 19/RD/PHE | 02/01/2025 | 02/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 14.82 | 0 | 0 | 100
20 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Ancillary works regarding Inter Connection of rising main with Teube-well with construction of boundary wall for additional land for Augmentation of Sasan PWSS at Hemtabad Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000654/2024-2025 | 416/RD/PHE | 29/01/2025 | 15/03/2025 | BHOLA PAUL | 14.33 | 0 | 0 | 0
21 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Ancillary Works Regarding Interconnection of Rising Main With Tubewell of Sasan PWSS at Headwork Site & 2nd TW Site In Connection with Sasan Augmentation at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000053/2025-2026 | 1543/RD/PHE | 11/06/2025 | 11/07/2025 | M/S CHOUDHURY CONSTRUCTION | 1.35 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | SM/10040 | Augmentation | Ancillary works and inter connection b/w rising main and OHR, I.C.W. Augmentation of Sasan PWSS at Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000401/2025-2026 | 1607/RD/PHE | 17/06/2025 | 12/06/2026 | SANDIP SARKAR | 3.79 | 0 | 0 | 100
Total | [13 empty] | 308.39 | 181.56 | 58.87