## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Sinking 3(Three) nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 250mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for CHOPRA and its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000469/2021-2022 | 396/RD/PHE | 10/02/2022 | 03/03/2022 | HAQUE CONSTRUCTION | 47.3 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Laying Distribution System for CHOPRA and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000648/2021-2022 | 394/RD/PHE | 10/02/2022 | 27/03/2022 | M/S J.S.B ASSOCIATE CONSTRUCTION | 228.06 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Soil Investigation for Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir For Augmentation of Chopra W/S Scheme In Chopra Block In Uttar Dinajpur District. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000048/2022-2023 | 1240/RD/PHE | 20/06/2022 | 10/07/2022 | G. MITRA & ASSOCIATES | 2.39 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000128/2022-2023 | 1520\RD | 24/08/2022 | 31/08/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000130/2022-2023 | 1536\RD | 25/08/2022 | 01/09/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 2007/RD/PHE | 16/11/2022 | 16/11/2022 | Resource Division | 147.27 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | xerox bill |  |  | VCH/001764/2022-2023 | BP-2022-23-211 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | xerox bill |  |  | VCH/001767/2022-2023 | BP-2022-23-209 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for CHOPRA (augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000468/2021-2022 | 395/RD/PHE | 10/02/2022 | 27/03/2022 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 1.57 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Chopra piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000233/2022-2023 | 366/RD/PHE | 07/02/2023 | 24/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.1 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Construction of Pump House (without Toilet) at 3rd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000234/2022-2023 | 367/RD/PHE | 07/02/2023 | 24/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chopra , C.C.C of Chopra in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000036/2023-2024 | 4003147552 | 28/04/2023 | 27/07/2023 | W.B.S.E.D.C.LTD | 5.16 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Approach Road including earthwork for roads at 2nd & 3rd Tube Well Site of Chopra Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000183/2022-2023 | 2253/RD/PHE | 22/12/2022 | 11/01/2023 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.19 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 639/RD/PHE | 23/03/2022 | 23/03/2022 | Resource Division | 126.92 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1514/RD/PHE | 22/08/2022 | 22/08/2022 | Resource Division | 19.32 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Providing Functional household Tap Connection for Chopra Water Supply Scheme (under Augmentation) at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000053/2022-2023 | 1272/RD/PHE | 24/06/2022 | 27/09/2025 | UTTAM SAHA | 119.51 | 0 | 0 | 65
17 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000875/2022-2023 | 2413/MLMD | 26/09/2022 | 25/12/2022 | HANNAN BUILDERS PVT. LTD. | 10.76 | 0 | 0 | 100
18 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000876/2022-2023 | 2414/MLMD | 26/09/2022 | 25/12/2022 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 10.97 | 0 | 0 | 100
19 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000874/2022-2023 | 2412/MLMD | 26/09/2022 | 25/12/2022 | HANNAN BUILDERS PVT. LTD. | 10.76 | 0 | 0 | 100
20 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000232/2022-2023 | 365/RD/PHE | 07/02/2023 | 24/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 5.04 | 0 | 0 | 100
21 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | hiring of inspection vehicle |  |  | BILL/01129/2023-2024 | BP-2023-24-279 | 16/02/2024 | 16/02/2024 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Construction of Over Head Reservoir(Capacity-600 Cum) of CHOPRA Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000382/2022-2023 | 736/RD/PHE | 15/03/2023 | 14/03/2024 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 188.99 | 0 | 0 | 80
23 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
24 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under Augmentation of Chopra PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer,Junior Engineer, ISD | ORD/000158/2024-2025 | 2890/RD/PHE | 25/09/2024 | 19/12/2025 | MOTI INDUSTRIES | 39.68 | 0 | 0 | 50
25 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Balance work for Pipeline crossing, earth filling & other ancillary works at CHOPRA Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000029/2024-2025 | 1689/RD/PHE | 10/06/2024 | 25/07/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.38 | 0 | 0 | 0
26 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Laying additional pipe line with FHTC for Augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000154/2024-2025 | 2886/RD/PHE | 25/09/2024 | 09/11/2024 | UTTAM SAHA | 37.35 | 0 | 0 | 0
27 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000523/2024-2025 | 95/RD/PHE | 08/01/2025 | 08/07/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0 | 0 | 100
28 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Providing FHTC in connection with augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000501/2024-2025 | 46/RD/PHE | 03/01/2025 | 17/02/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.43 | 0 | 0 | 0
29 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Laying of additional pipeline for improving FHTC at different mouzas at Chopra Piped Water Supply Scheme (In Connection with Augmentation of Chopra PWSS) under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000142/2024-2025 | 2838/RD/PHE | 23/09/2024 | 23/10/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.83 | 0 | 0 | 0
30 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Construction Of Boundary Wall With Gate at 3rd Tube-Well Site in connection with Augmentation of Chopra PWSS at Chopra Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000344/2024-2025 | 3297/RD/PHE | 20/11/2024 | 05/01/2025 | M C CONSTRUCTION | 5.55 | 0 | 0 | 100
31 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Chopra Water Supply Scheme. | SM/10129 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chopra Water Supply Scheme (Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 105 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000358/2025-2026 | 2504/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.83 | 0 | 0 | 0
Total | [13 empty] | 1141.44 | 0 | 0