## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) | SM/10424 | Retrofitting | Restoration of damaged Pipe Line work required for FHTC work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Divion, P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000442/2021-2022 | 2319/RD/PHED | 09/12/2021 | 23/01/2022 | M/S P.S. ENTERPRISE | 10.21 | 9.91 | 97.04 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) | SM/10424 | Retrofitting | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000038/2022-2023 | 1050/RD/PHED | 12/05/2022 | 26/06/2022 | TAPAN KUMAR MAJUMDER | 14.06 | 4.15 | 29.55 | 1
Total | [13 empty] | 24.27 | 14.06 | 57.95