## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10426 | Retrofitting | Restoration of Pipeline for Providing FHTC of Gunabari Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000034/2022-2023 | 1046/RD/PHED | 12/05/2022 | 26/06/2022 | M/S.SADHANA ENTERPRISE | 10.26 | 10.07 | 98.21 | 1
Total | [13 empty] | 10.26 | 10.07 | 98.21