## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Sripur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10441 | Retrofitting | Restoration of pipe line for providing FHTC for Sripur water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | Assistant Engineer RSD |  | ORD/000021/2022-2023 | 1033/RD/PHED | 12/05/2022 | 11/06/2022 | UJJAL KUMAR SARKAR | 5.15 | 5.15 | 99.97 | 100
Total | [13 empty] | 5.15 | 5.15 | 99.97