## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Sahavita Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10443 | Retrofitting | Restoration of pipe line for providing FHTC for Sahavita water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000030/2022-2023 | 1042/RD/PHED | 12/05/2022 | 11/06/2022 | BITTU ENTERPRISE | 8.68 | 0 | 0 | 1
Total | [13 empty] | 8.68 | 0 | 0