## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) | SM/10444 | Retrofitting | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Mahammadpur(Surun) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD |  | ORD/000285/2022-2023 | 499/RD/PHE | 17/02/2023 | 03/04/2023 | M/S DUTTA ENTERPRISE (JAYANTAJKD.USE@GMAIL.COM) | 9.08 | 5.35 | 58.9 | 0
Total | [13 empty] | 9.08 | 5.35 | 58.9