## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Bamair Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10493 | Retrofitting | Restoration of Pipe Line for Providing FHTC for Bamir Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000045/2022-2023 | 1009/RD/PHED | 11/05/2022 | 31/05/2022 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.51 | 0 | 0 | 1
Total | [13 empty] | 3.51 | 0 | 0