## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10499 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur. (Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000031/2022-2023 | 1043/RD/PHED | 12/05/2022 | 11/06/2022 | DAS CONSTRUCTION COMPANY | 7.82 | 7.73 | 98.89 | 100
Total | [13 empty] | 7.82 | 7.73 | 98.89