## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10500 | Retrofitting | Restoration of Pipe line for providing FHTC for Noabari(Kunore) Pipe Water Supply Scheme of Kaliaganj Block in the District of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000560/2022-2023 | 1024/RD/PHE | 31/03/2023 | 30/04/2023 | BHOWMICK ENTERPRISE | 0.91 | 0.91 | 99.74 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10500 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Noabari(Baruna) Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD |  | ORD/000559/2022-2023 | 1022/RD/PHE | 31/03/2023 | 15/05/2023 | ANILA CONSTRUCTION | 11.49 | 11.41 | 99.35 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) | SM/10500 | Retrofitting | charges for vehicle inspection |  |  | BILL/01127/2023-2024 | BP-2023-24-281 | 16/02/2024 | 16/02/2024 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
Total | [13 empty] | 12.8 | 12.32 | 96.27