## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Kamartor Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000014/2022-2023 | 1026/RD/PHED | 12/05/2022 | 26/06/2022 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 23.5 | 22.09 | 93.99 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Purba Chutiakhore Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000018/2022-2023 | 1030/RD/PHED | 12/05/2022 | 26/06/2022 | M/S LUCKY CONSTRUCTION | 46.82 | 37.99 | 81.15 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Amalbari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000011/2022-2023 | 1023/RD/PHED | 12/05/2022 | 26/06/2022 | KARTICK BISWAS | 13.46 | 13.09 | 97.25 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Butijhari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000007/2022-2023 | 1019/RD/PHE | 12/05/2022 | 26/06/2022 | CHAITANYA SAMAL | 10.67 | 10.55 | 98.9 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying additional Pipe Line for Providing Functional Household Tap Connection of Faridpur Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000009/2022-2023 | 1021/RD/PHED | 12/05/2022 | 26/06/2022 | TAPAN KUMAR MAJUMDER | 11.27 | 11.13 | 98.75 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying Additional Pipe Line Beyond the scope of Pipeline to be laid as per DPR Purba Rampur Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000015/2022-2023 | 1027/RD/PHED | 12/05/2022 | 26/06/2022 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 27.28 | 27.27 | 99.96 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Dehar Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000013/2022-2023 | 1025/RD/PHED | 12/05/2022 | 26/06/2022 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 21.86 | 21.68 | 99.17 | 1
8 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Khowaspur Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000010/2022-2023 | 1022/RD/PHED | 12/05/2022 | 26/06/2022 | DIPANKAR SARKAR | 12.85 | 12.22 | 95.13 | 1
9 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000038/2022-2023 | 1050/RD/PHED | 12/05/2022 | 26/06/2022 | TAPAN KUMAR MAJUMDER | 14.06 | 9.9 | 70.42 | 1
10 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Bhojpur Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000016/2022-2023 | 1028/RD/PHED | 12/05/2022 | 26/06/2022 | M/S PIONEER ENTERPRISE | 31.81 | 31.3 | 98.4 | 1
11 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Restoration of Damaged Pipe line work required for FHTC Work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte.(PART -B) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000180/2022-2023 | 2250/RD/PHE | 22/12/2022 | 11/01/2023 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 10.28 | 10.01 | 97.38 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying Additional Pipe Line for Providing Functional Household Tap Connection of Puria Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000012/2022-2023 | 1024/RD/PHED | 12/05/2022 | 26/06/2022 | NIMAI DAS | 18.89 | 18.38 | 97.32 | 1
13 | UTTAR DINAJPUR |  | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Amaljhari Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000019/2022-2023 | 1031/RD/PHED | 12/05/2022 | 11/06/2022 | APEX ENTERPRISES | 8.95 | 6.73 | 75.22 | 100
Total | [13 empty] | 251.69 | 232.35 | 92.31