## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Restoration of Pipe Line for providing FHTC at Jaingaon Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) | SM/10547 | Retrofitting | Restoration of Pipe Line for providing F.H.T.C. at Jaingaon Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000036/2022-2023 | 1048/RD/PHED | 12/05/2022 | 26/06/2022 | SAHA CONSTRUCTION | 13.7 | 13.36 | 97.49 | 100
Total | [13 empty] | 13.7 | 13.36 | 97.49