## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Augmentation work of Dhulahar Water Supply Scheme at Ithar Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000074/2022-2023 | 1373/RD/PHE | 14/07/2022 | 12/10/2022 | M/S LOKENATH CONSTRUCTION | 118.85 | 68.82 | 57.9 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Dhulahar Water Supply Scheme at Itahar Block Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD |  | ORD/000268/2022-2023 | 432/RD/PHE | 10/02/2023 | 27/03/2023 | M/S PRIME BUILDERS PRIME.BUILDERS@GMAIL.COM | 3.51 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Supply, delivery, installation, commissioning of electro-mechanical components of Augmentation of Dhulahar Water Supply Scheme TW no I in the District of Uttar dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001104/2022-2023 | 422/MLMD | 14/03/2023 | 12/06/2023 | JIBU SINGHA | 10.18 | 10.17 | 99.87 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Supply, delivery, installation, commissioning of electro-mechanical components of Augmentation of Dhulahar Water Supply Scheme TW no II in the District of Uttar dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001105/2022-2023 | 423/MLMD | 14/03/2023 | 12/06/2023 | ALPHA ENTERPRISE. | 10.08 | 10.08 | 100 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of DHULAHAR Pipe Water Supply Scheme in connection with Augmentation at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000327/2022-2023 | 656/RD/PHE | 03/03/2023 | 29/10/2023 | M/S PIONEER ENTERPRISE | 84.9 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1950/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 10.93 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1944/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 7.27 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | FHTC (Functional Household Tap Connection) for Dhulahar Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000160/2022-2023 | 2020/RD/PHE | 17/11/2022 | 16/01/2023 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 35.2 | 33.03 | 93.84 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | hiring of inspection vehicle |  |  | BILL/01130/2023-2024 | BP-2023-24-282 | 16/02/2024 | 16/02/2024 | DEBASISH GHOSH | 0.2 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | SM/10548 | Augmentation | Construction of Approach Road, Laying of Pipe Line,Fhtc And Other Allied Works Of Dhulahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000404/2024-2025 | 3574/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.88 | 0 | 0 | 0
Total | [13 empty] | 318 | 122.09 | 38.39