## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. | SM/10615 | Support-WQMSP | PAYMENT FOR QUALITY COUNCIL OF INDIA ACCREDITATION FEE FOR UTTAR DINAJPUR DISTRICT LABORATORY | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000078/2022-2023 | 1376/RD/1 | 15/07/2022 | 14/08/2022 | DULAL MAJUMDER | 0.28 | 0.28 | 100 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. | SM/10615 | Support-WQMSP | PAYMENT FOR QUALITY COUNCIL OF INDIA FOR ACCREDITATION FEE FOR UTTAR DINAJPUR DISTRICT LABORATORY UNDER RAIGANJ DIVISION,P.H.E.DTE. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000076/2022-2023 | 1376/RD | 15/07/2022 | 15/07/2023 | DULAL MAJUMDER | 0.28 | 0.25 | 89.58 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. | SM/10615 | Support-WQMSP | Document review charge(NABL) & dist lab raiganj(green economy |  |  | VCH/000627/2022-2023 | BP-2022-23-83 | 22/06/2022 | 22/06/2022 | DULAL MAJUMDER | 0.09 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. | SM/10615 | Support-WQMSP | Balance allied works of Up-Gradation of Uttar Dinajpur District Laboratory in connection with NABL at Raiganj PHE Complex under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000050/2025-2026 | 1482/RD/PHE | 04/06/2025 | 04/07/2025 | DULAL MAJUMDER | 1.4 | 0 | 0 | 100
Total | [13 empty] | 2.05 | 0.54 | 26.13