## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1975/RD/PHE | 08/11/2022 | 08/11/2022 | Resource Division | 70.56 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Restoration of road for laying of water pipeline along and across the Kanki-Goagaon Road at different stretches under Chakulia PWSS under Raiganj Division, P.H.E.Dte. |  |  | BILL/00020/2022-2023 |  | 07/12/2022 | 07/12/2022 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of CHAKULIA Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000371/2022-2023 | 728/RD/PHE | 15/03/2023 | 14/03/2024 | MD HAKIMUDDIN | 165.54 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chakulia, Kanki C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000090/2023-2024 | 4003131653 | 24/05/2023 | 22/08/2023 | W.B.S.E.D.C.LTD | 6.29 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation |  |  |  | BILL/00072/2022-2023 | BP-2022-23-264 | 30/12/2022 | 30/12/2022 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | FHTC (Functional Household Tap Connection) for Chakulia Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000156/2022-2023 | 2016/RD/PHE | 17/11/2022 | 15/02/2023 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80 | 0 | 0 | 65
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01219/2023-2024 | BP-2024-25-25 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 0.15 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Augmentation of CHAKALIA Water Supply Scheme at Goalpokhar-II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000075/2022-2023 | 1407/RD/PHE | 25/07/2022 | 31/12/2024 | SANYAL ENTERPRISE | 248.78 | 0 | 0 | 85
9 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components and making compound lighting arrangement at T/W no. I of Augmentation of Chakulia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009723) | Assistant Engineer - I | Junior Engineer-02 | ORD/001095/2022-2023 | 266/MLMD | 24/02/2023 | 12/10/2025 | KARMAKAR CONSTRICTION. | 13.73 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Providing FHTC in connection with augmentation of Chakulia Pipe Water Supply Scheme at Goalpokher-II Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000506/2024-2025 | 51/RD/PHE | 03/01/2025 | 17/02/2025 | AJIT PRAMANIK | 15.76 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Chakulia PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000159/2024-2025 | 2891/RD/PHE | 25/09/2024 | 06/08/2025 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 44.17 | 0 | 0 | 75
12 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Restoration of damaged pipeline due Culvert, Drain & PCC Road Construction with ancillary works at various mouzas in connection with Augmentation of Chakulia PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000134/2024-2025 | 3024/RD/PHE | 03/10/2024 | 02/12/2024 | SANYAL ENTERPRISE | 20.59 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | SM/11196 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II & III of Chakulia Water Supply Scheme in the District of Utter Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009723) | Assistant Engineer - I | Junior Engineer-02 | ORD/001101/2022-2023 | 268/MLMD | 24/02/2023 | 14/06/2024 | JIBU SINGHA | 20.69 | 0 | 0 | 100
Total | [13 empty] | 689.64 | 0 | 0