## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I,Goalpokhar-II,Hemtabad | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11516 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Goalpokhor-ll & Goalpokhor-I, Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000035/2023-2024 | 1501/RD/PHE | 19/05/2023 | 19/08/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 432.57 | 0 | 0 | 2
2 | UTTAR DINAJPUR | Goalpokhar-I,Goalpokhar-II,Hemtabad | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11516 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Itahara village under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000150/2024-2025 | 2882/RD/PHE | 25/09/2024 | 24/03/2025 | MAA SHEETALA ENTERPRISE | 40.1 | 0 | 0 | 0
Total | [13 empty] | 472.67 | 0 | 0