## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad,Islampur,Itahar | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. | SM/11517 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Hemtabad, Islampur & Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | JUNIOR ENGINEER,Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000022/2023-2024 | 1284/RD/PHE | 08/05/2023 | 01/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 709.96 | 9.51 | 1.34 | 50
2 | UTTAR DINAJPUR | Hemtabad,Islampur,Itahar | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. | SM/11517 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Patnihar village under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000149/2024-2025 | 593/RD/PHE | 19/02/2025 | 20/04/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.7 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad,Islampur,Itahar | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. | SM/11517 | New | Payment of quotations against three (03) nos. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Itahar CCC) for energization of 1. Naldanga, 2. Nagua, & 3. Tiarbati Mini-PWSS against SM/11517 under Raiganj Division, PHE Dte. Uttar Dinajpur |  |  | BILL/00659/2024-2025 | BP-2024-25-406 | 24/03/2025 | 24/03/2025 | W.B.S.E.D.C.L | 0.29 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Hemtabad,Islampur,Itahar | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. | SM/11517 | New | Payment of quotations against two (02) nos. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Hemtabad CCC) for energization of 1.Pirojpur & 2.Sekhpura Mini-PWSS against SM/11517 under Raiganj Division, PHE Dte., Uttar Dinajpur. |  |  | BILL/00779/2024-2025 |  | 18/03/2025 | 18/03/2025 | W.B.S.E.D.C.L | 8.83 | 0 | 0 | 0
Total | [13 empty] | 762.79 | 9.51 | 1.25