## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar,Kaliaganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Balahar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000151/2024-2025 | 2883/RD/PHE | 25/09/2024 | 24/11/2024 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 43.71 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Itahar,Kaliaganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Chakbhabanipur village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000152/2024-2025 | 2884/RD/PHE | 25/09/2024 | 24/11/2024 | M/S. B. PAUL & COMPANY | 40.94 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar,Kaliaganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Itahar & Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000023/2023-2024 | 1285/RD/PHE | 08/05/2023 | 02/01/2026 | UJJWAL DAS | 503.04 | 19.16 | 3.81 | 20
4 | UTTAR DINAJPUR | Itahar,Kaliaganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11518 | New | Payment of quotations against one (01) no. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Kaliyaganj CCC) for energization of Baje Dhabail Mini-PWSS against SM/11518 under Raiganj Division, PHE Dte., Uttar Dinajpur. |  |  | BILL/00215/2025-2026 |  | 15/05/2025 | 15/05/2025 | W.B.S.E.D.C.L | 4.94 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar,Kaliaganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11518 | New | Payment of quotations against two (02) nos. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Kaliyaganj CCC) for energization of 1. Mahatair & 2. Haldibari Mini PWSS against SM/11518 under Raiganj Division, PHE Dte. Uttar Dinajpur. |  |  | BILL/00768/2024-2025 | BP-2024-25-414 | 27/03/2025 | 27/03/2025 | W.B.S.E.D.C.L | 11.88 | 0 | 0 | 0
Total | [13 empty] | 604.51 | 19.16 | 3.17