## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj,Karandighi | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11519 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Kaliyaganj & Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000024/2023-2024 | 1286/RD/PHE | 08/05/2023 | 02/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 616.73 | 38.04 | 6.17 | 15
2 | UTTAR DINAJPUR | Kaliaganj,Karandighi | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11519 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Kaluhar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000153/2024-2025 | 2885/RD/PHE | 25/09/2024 | 24/11/2024 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 40.07 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Kaliaganj,Karandighi | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11519 | New | Payment of quotations against One(01) no. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Kaliyaganj CCC) for energization of 1. Khiltor Mini PWSS against SM/11519 under Raiganj Division, PHE Dte. Uttar Dinajpur. |  |  | BILL/00844/2024-2025 |  | 27/03/2025 | 27/03/2025 | W.B.S.E.D.C.L | 5.4 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj,Karandighi | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11519 | New | Payment of quotations against One(01) no. of Mini-PWSS served by W.B.S.E.D.C.L Ltd. (Kaliyaganj CCC) for energization of 1. bijali Mini PWSS against SM/11519 under Raiganj Division, PHE Dte. Uttar Dinajpur. |  |  | BILL/00769/2024-2025 | BP-2024-25-410 | 27/03/2025 | 27/03/2025 | W.B.S.E.D.C.L | 2.95 | 0 | 0 | 0
Total | [13 empty] | 665.15 | 38.04 | 5.72