## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra,Goalpokhar-II | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11520 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Chopra & Goalpokhor-II Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000021/2023-2024 | 1283/RD/PHE | 08/05/2023 | 08/08/2023 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 656.06 | 15.82 | 2.41 | 30
Total | [13 empty] | 656.06 | 15.82 | 2.41