## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi,Raiganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11521 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Karandighi & Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer,Junior Engineer, RWS | ORD/000025/2023-2024 | 1287/RD/PHE | 08/05/2023 | 08/03/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 206.76 | 14.16 | 6.85 | 5
2 | UTTAR DINAJPUR | Karandighi,Raiganj | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | SM/11521 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Jugiamer village under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000148/2024-2025 | 2880/RD/PHE | 25/09/2024 | 24/11/2024 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.97 | 0 | 0 | 0
Total | [13 empty] | 250.73 | 14.16 | 5.65