## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Gouri PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000005/2023-2024 | 4003132438 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Gouri PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000006/2023-2024 | 4003132554 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1957/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 46.51 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of GOURI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000190/2023-2024 | 1673/MLMD | 28/06/2023 | 26/09/2023 | DAS ENTERPRISE. | 11.9 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of GOURI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000191/2023-2024 | 1674/MLMD | 28/06/2023 | 26/09/2023 | DILIP MAHATO. | 11.95 | 0 | 0 | 100
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Implementation of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000094/2022-2023 | 1541/RD/PHE | 26/08/2022 | 09/11/2024 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 376.23 | 0 | 0 | 56
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Construction Over Head Resorvoir (OHR) and other allied works of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000019/2023-2024 | 1281/RD/PHE | 08/05/2023 | 02/01/2026 | UTTAM SAHA | 240.92 | 0 | 0 | 50
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Making compound lighting arrangement with allied works at T/W no. I of Gouri Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011695) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000712/2023-2024 | 2242/MLMD | 18/07/2023 | 30/01/2026 | M/S SABANA CONSTRUCTION | 2.64 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gouri PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000479/2024-2025 | 12/RD/PHE | 02/01/2025 | 16/02/2025 | M/S P.S. ENTERPRISE | 88.14 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Trial Run For Gouri PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000691/2024-2025 | 536/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOURI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000460/2023-2024 | 568/RD/PHE | 05/03/2024 | 16/10/2024 | M/S BARENDRA CONSTRUCTION | 22.58 | 0 | 0 | 70
Total | [13 empty] | 807.93 | 0 | 0