## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Making compound lighting arrangement with allied works at T/W no. I of Baghan Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011707) | Assistant Engineer - I | Junior Engineer-07 | ORD/000707/2023-2024 | 2237/MLMD | 18/07/2023 | 16/10/2023 | SHREE BISHNU CONSTRUCTION | 2.64 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | W.B.S.E.D.C.LTD Quotation charge at P/H-I of Baghan, of Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001069/2022-2023 | 4003074327 | 01/02/2023 | 02/05/2023 | W.B.S.E.D.C.LTD | 0.84 | 0 | 0 | 1
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | W.B.S.E.D.C.LTD Quotation charge at P/H-II of Baghan, of Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001070/2022-2023 | 4003074355 | 01/02/2023 | 02/05/2023 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 1
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1956/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 28.75 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Construction of OHR & other allied works of BAGHAN and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000318/2022-2023 | 589/RD/PHE | 24/02/2023 | 01/01/2026 | PRASANTA DUTTA | 137.78 | 0 | 0 | 61
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Additional Pipe Line For Providing FHTC at Baghan PWSS at Kaliaganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte.(New PWSS) | Assistant Engineer RSD |  | ORD/000033/2024-2025 | 1694/RD/PHE | 10/06/2024 | 25/07/2024 | PRASANTA DUTTA | 9.75 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAGHAN Water Supply Scheme T/W no. II in the District of Uttar Dinajpur | Assistant Engineer - I | Junior Engineer-07 | ORD/001090/2022-2023 | 261/MLMD | 24/02/2023 | 25/05/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 12.99 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAGHAN Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001089/2022-2023 | 260/MLMD | 24/02/2023 | 25/05/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 12.99 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Wayleave/track crossing proposal with application ID:NFR-KIR-2024-WL-08 under katihar division of northeast frontier railway in connection with Baghan PWSS in kaliyaganj block under Raiganj division PHE Dte. |  |  | BILL/00156/2024-2025 | BP-2024-25-103 | 09/07/2024 | 09/07/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-08 under Katihar Division of Northeast Frontier Railway in connection with Baghan PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. |  |  | BILL/00099/2024-2025 | BP-2024-25-67 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER | 0.11 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Implementation of Baghan and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division , PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000079/2022-2023 | 1507/RD/PHE | 18/08/2022 | 01/01/2026 | PRASANTA DUTTA | 121.02 | 0 | 0 | 70
12 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAGHAN Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000458/2023-2024 | 566/RD/PHE | 05/03/2024 | 14/04/2025 | M/S P.S. ENTERPRISE | 22.76 | 0 | 0 | 80
13 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Trial Run For Baghan PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000705/2024-2025 | 544/RD/PHE | 12/02/2025 | 13/05/2025 | PRASANTA DUTTA | 0.88 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 | New | Jack Pushing of M.S. Pipe of 200 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 37/8 to 37/9 near Kaliyaganj Railway Station (KAJ) for Baghan and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000145/2024-2025 | 2832/RD/PHE | 23/09/2024 | 18/04/2025 | RAY CONSTRUCTION &CO. | 27.72 | 0 | 0 | 100
Total | [13 empty] | 385.07 | 0 | 0