## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000012/2023-2024 | 4003137386 | 18/04/2023 | 03/05/2023 | W.B.S.E.D.C.LTD | 0.5 | 0.5 | 100 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000011/2023-2024 | 4003132926 | 16/04/2023 | 01/05/2023 | W.B.S.E.D.C.LTD | 0.55 | 0.55 | 100 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1955/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 30.7 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. |  |  | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 29/09/2023 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001103/2022-2023 | 421/MLMD | 14/03/2023 | 12/06/2023 | M/S PARIMAL DAS. | 10.92 | 10.84 | 99.3 | 100
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001102/2022-2023 | 420/MLMD | 14/03/2023 | 12/06/2023 | M/S. KUNDU CONSTRACTION | 10.89 | 10.8 | 99.2 | 100
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Construction of OHR & other allied works of BAJE BINDOL and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000312/2022-2023 | 587/RD/PHE | 24/02/2023 | 01/04/2025 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 157.71 | 47.44 | 30.08 | 85
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAJE BINDOL Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000461/2023-2024 | 569/RD/PHE | 05/03/2024 | 01/03/2025 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 22.76 | 0 | 0 | 75
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Trial Run For Baje Bindol PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000697/2024-2025 | 538/RD/PHE | 12/02/2025 | 13/05/2025 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Implementation of BAJE BINDOLE and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000093/2022-2023 | 1540/RD/PHE | 26/08/2022 | 17/05/2024 | M/S MAA TARA CONSTRUCTION | 239.58 | 216.75 | 90.47 | 100
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Additional Pipe Line for Providing FHTC Baje Bindol Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000124/2024-2025 | 3014/RD/PHE | 03/10/2024 | 01/01/2025 | M/S MAA TARA CONSTRUCTION | 54.09 | 0 | 0 | 60
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Order for supply and delivery of Canon Genuine Toner NPG-59 Black & Toner Cartridge for Printer to the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. |  |  | BILL/00815/2024-2025 | BP-2024-25-471 | 29/03/2025 | 29/03/2025 | AYANTIKA ENTERPRISE | 0.09 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Order for supply and delivery of Canon Genuine Toner NPG-59 Black & Toner Cartridge for Printer to the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. |  |  | BILL/00816/2024-2025 | BP-2024-25-470 | 29/03/2025 | 29/03/2025 | AYANTIKA ENTERPRISE | 0.06 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Order for supply and delivery of Canon Drum Unit Set 2002 (compatible) to the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. |  |  | BILL/00819/2024-2025 | BP-2024-25-467 | 29/03/2025 | 29/03/2025 | AYANTIKA ENTERPRISE | 0.05 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Arrangement for payment of Mutation fees through Grips e-Challan in favour of Land & Land Reforms Department, Govt. of West Bengal under Uttar Dinajpur District. |  |  | BILL/00727/2024-2025 | BP-2024-25-441 | 27/03/2025 | 27/03/2025 | M/S MANDAL ENTERPRISE | 0.08 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Order for supply and delivery of Canon Genuine Toner NPG-59 & NPG-51 Black to the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. |  |  | BILL/00817/2024-2025 | BP-2024-25-469 | 29/03/2025 | 29/03/2025 | AYANTIKA ENTERPRISE | 0.07 | 0 | 0 | 0
17 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Order for supply and delivery of Canon Drum Unit Set 2520 (compatible) to the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. |  |  | BILL/00818/2024-2025 | BP-2024-25-468 | 29/03/2025 | 29/03/2025 | AYANTIKA ENTERPRISE | 0.06 | 0 | 0 | 0
18 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Making compound lighting arrangement with allied works at T/W no. I of Baje Bindole Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011708) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000710/2023-2024 | 2240/MLMD | 18/07/2023 | 01/07/2025 | MUKHERJEE ART CENTRE | 3.83 | 0 | 0 | 0
19 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 560.33 | 286.88 | 51.2