## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Making compound lighting arrangement with allied works at T/W no. I of Baje Bindole Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011708) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000710/2023-2024 | 2240/MLMD | 18/07/2023 | 16/10/2023 | MUKHERJEE ART CENTRE | 3.83 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000012/2023-2024 | 4003137386 | 18/04/2023 | 03/05/2023 | W.B.S.E.D.C.LTD | 0.5 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000011/2023-2024 | 4003132926 | 16/04/2023 | 01/05/2023 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1955/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 30.7 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. |  |  | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 29/09/2023 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001103/2022-2023 | 421/MLMD | 14/03/2023 | 12/06/2023 | M/S PARIMAL DAS. | 10.92 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001102/2022-2023 | 420/MLMD | 14/03/2023 | 12/06/2023 | M/S. KUNDU CONSTRACTION | 10.89 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Construction of OHR & other allied works of BAJE BINDOL and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000312/2022-2023 | 587/RD/PHE | 24/02/2023 | 01/04/2025 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 157.71 | 0 | 0 | 85
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAJE BINDOL Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000461/2023-2024 | 569/RD/PHE | 05/03/2024 | 01/03/2025 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 22.76 | 0 | 0 | 75
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Trial Run For Baje Bindol PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000697/2024-2025 | 538/RD/PHE | 12/02/2025 | 13/05/2025 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Implementation of BAJE BINDOLE and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000093/2022-2023 | 1540/RD/PHE | 26/08/2022 | 17/05/2024 | M/S MAA TARA CONSTRUCTION | 239.58 | 0 | 0 | 100
Total | [13 empty] | 500.84 | 0 | 0