## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000231/2022-2023 | 364/RD/PHE | 07/02/2023 | 24/03/2023 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.12 | 4.11 | 99.96 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000567/2022-2023 | 1030/RD/PHE | 31/03/2023 | 15/05/2023 | M/S SANTI TRADERS | 5.03 | 5.02 | 99.78 | 100
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Karandighi, Zone-I, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | ORD/001158/2022-2023 | 4003118815 | 26/03/2023 | 02/04/2023 | W.B.S.E.D.C.LTD | 0.73 | 0.73 | 100 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 1945/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 112.29 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Karandighi Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000334/2024-2025 | 3290/RD/PHE | 20/11/2024 | 20/12/2024 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 15.76 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Augmentation of KARANDIGHI(Zone-I)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000118/2022-2023 | 1670/RD/PHE | 05/09/2022 | 04/12/2022 | DIPESH BHOWMIK | 196.21 | 194.93 | 99.35 | 100
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Making compound lighting arrangement with allied works at T/W no. I of Karandighi Water Supply Scheme, (Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011651) | Assistant Engineer - I | Junior Engineer-02 | ORD/000261/2023-2024 | 2234/MLMD | 18/07/2023 | 16/10/2023 | SUBHAS CHANDRA KESHORI | 2.33 | 2.28 | 98.11 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01223/2023-2024 | BP-2024-25-24 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 14.86 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | FHTC (Functional Household Tap Connection) for Karandighi Zone-I Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000170/2022-2023 | 2030/RD/PHE | 17/11/2022 | 29/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.36 | 40.99 | 51.01 | 70
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Laying additional pipe line with FHTC for Augmentation Of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000465/2024-2025 | 3783/RD/PHE | 19/12/2024 | 28/01/2026 | BHOLA PAUL | 46.07 | 0 | 0 | 60
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Providing FHTC in connection with augmentation of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000502/2024-2025 | 47/RD/PHE | 03/01/2025 | 17/02/2025 | M/S P.S. ENTERPRISE | 25.35 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-I Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000355/2025-2026 | 2501/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 19.35 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-I) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001046/2022-2023 | 247/MLMD | 24/02/2023 | 28/06/2024 | DEY ENTERPRISE [HOWRAH] | 12.62 | 9.53 | 75.47 | 100
15 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-I) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001045/2022-2023 | 246/MLMD | 24/02/2023 | 12/05/2024 | DIPALI CONSTRUCTION. | 12.45 | 11.31 | 90.84 | 100
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11721 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of KARANDIGHI(Zone-I) Pipe Water Supply Scheme at in connection with Augmentation Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000370/2022-2023 | 727/RD/PHE | 15/03/2023 | 01/07/2025 | M/S ELITE CONSTRUCTION | 165.61 | 0 | 0 | 90
Total | [13 empty] | 717.93 | 268.9 | 37.45