## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Augmentation work of LAKHIPUR and it's adjoining mouzas Piped Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000098/2022-2023 | 1545/RD/PHE | 26/08/2022 | 24/11/2022 | UTTAM SAHA | 194.17 | 164 | 84.46 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000266/2022-2023 | 406/RD/PHE | 09/02/2023 | 26/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.95 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Repairing of Pump House at 2nd Tubewell Site in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000244/2022-2023 | 375/RD/PHE | 07/02/2023 | 24/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.09 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Construction of Over Head Reservoir(Capacity-450 Cum) of LAKHIPUR Pipe Water Supply Scheme in connection with Augmentation at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000384/2022-2023 | 737/RD/PHE | 15/03/2023 | 14/03/2024 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 158.66 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Lakhipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011434) | Assistant Engineer - I |  | ORD/000622/2023-2024 | 2659/MLMD | 10/08/2023 | 06/11/2028 | MAA BHABOTARINE ENTERPRISE. | 10.54 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1946/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 26.53 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | FHTC (Functional Household Tap Connection) for Lakhipur Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000167/2022-2023 | 2027/RD/PHE | 17/11/2022 | 15/02/2023 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 79.41 | 60.05 | 75.62 | 45
8 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Lakhipur Water Supply Scheme TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000024/2023-2024 | 739/ MLMD | 20/04/2023 | 19/07/2023 | GHOSH BROTHERS... | 12.5 | 12.49 | 99.92 | 100
9 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Lakhipur Water Supply Scheme TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001165/2022-2023 | 518/MLMD | 20/03/2023 | 18/06/2023 | M/S. KUNDU CONSTRACTION | 12.5 | 12.47 | 99.81 | 100
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 28/06/2024 | DEBASISH GHOSH | 4.8 | 1.2 | 25 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation Of Lakhipur PWSS at Chopra Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000339/2024-2025 | 3295/RD/PHE | 20/11/2024 | 20/12/2024 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 8.59 | 0 | 0 | 70
12 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | SM/11724 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Lakhipur Water Supply Scheme (Aumentation)at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000393/2025-2026 | 1927/RD/PHE | 30/06/2025 | 27/12/2025 | KOHINOOR ALAM | 32.33 | 0 | 0 | 0
Total | [13 empty] | 547.07 | 250.21 | 45.74