## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Augmentation work of MARNAI and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000099/2022-2023 | 1546/RD/PHE | 26/08/2022 | 17/09/2025 | M/S LOKENATH CONSTRUCTION | 354.98 | 182.19 | 51.32 | 55
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | FHTC (Functional Household Tap Connection) for Marnai Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000169/2022-2023 | 2029/RD/PHE | 17/11/2022 | 15/02/2023 | M/S LOKENATH CONSTRUCTION | 79.34 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Marnai Water Supply Scheme at Itahar Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000267/2022-2023 | 407/RD/PHE | 09/02/2023 | 26/03/2023 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 3.53 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011419) | Assistant Engineer - I | Junior Engineer-02 | ORD/000221/2023-2024 | 2204/MLMD | 18/07/2023 | 30/07/2026 | MERCURY ENGINEERING COMPANY. | 10.53 | 0 | 0 | 81
5 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Marnai PWSS | Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000290/2023-2024 | 2363/RD/PHE | 11/08/2023 | 10/10/2023 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.02 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Marnai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011652) | Assistant Engineer - I | Junior Engineer-02 | ORD/001982/2023-2024 | 3872/MLMD | 18/12/2023 | 16/03/2029 | SHREE BISHNU CONSTRUCTION | 6.98 | 5.95 | 85.3 | 85
7 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011419) | Assistant Engineer - I | Junior Engineer-02 | ORD/000224/2023-2024 | 2205/MLMD | 18/07/2023 | 01/01/2025 | MANIK CHANDRA SAHA. | 10.38 | 9.1 | 87.67 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 12/RD/PHE | 04/01/2023 | 04/01/2023 | Resource Division | 58.04 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Construction of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Marnai Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000403/2024-2025 | 3573/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.84 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Supply, installation, commissioning and trial run of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02,Junior Engineer-07 | ORD/000317/2024-2025 | 2944/MLMD | 11/09/2024 | 10/12/2024 | S.P. ENTERPRISE (KOLKATA) | 10.56 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Quotation for new service connection at MARNAI PH-III (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00031/2024-2025 | BP-2024-25-62 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 6.97 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | SM/11725 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Marnai Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000280/2025-2026 | 2207/RD/PHE | 29/07/2025 | 25/01/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 33.6 | 0 | 0 | 0
Total | [13 empty] | 621.78 | 197.25 | 31.72