## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1944/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 33.97 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & III and installation of grid connection solar PV system with net metering at T/W no.- I of Goalpokher Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011422) | Assistant Engineer - I | Junior Engineer-02 | ORD/000170/2023-2024 | 2090/MLMD | 04/07/2023 | 29/12/2028 | DILIP MAHATO. | 27.26 | 0 | 0 | 65
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | FHTC (Functional Household Tap Connection) for Goalpokhar Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000166/2022-2023 | 2026/RD/PHE | 17/11/2022 | 15/02/2023 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 66.67 | 0 | 0 | 98
4 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Repairing for Head Work Site Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | Assistant Engineer ISD |  | ORD/000040/2023-2024 | 1539/RD/PHE | 24/05/2023 | 08/07/2023 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 2.35 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at Pole Shifting of Goalpokher PWS, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02548/2023-2024 | BP-2023-24-449 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 1.48 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Augmentation work of GOALPOKHAR and it's adjoining mouzas Piped Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000100/2022-2023 | 1547/RD/PHE | 26/08/2022 | 24/11/2022 | AJIT PARMANIK | 319.76 | 0 | 0 | 95
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of GOALPOKHER Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000380/2022-2023 | 735/RD/PHE | 15/03/2023 | 14/03/2025 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 165.64 | 0 | 0 | 85
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Repair and Maintenance of Boundary Wall and construction of Concrete Pathway at both Head work site and 2nd tube well Pump House site in connection with Augmentation of Goalpokhar Pipe W/S scheme under Islampur Sub-Division PHE Dte.under Raiganj Division, PHE Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000497/2024-2025 | 30/RD/PHE | 02/01/2025 | 16/02/2025 | HAQUE CONSTRUCTION | 8.16 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Laying of Additional Pipeline for Retrofitting in connection with augmentation of Goalpokhar Water Supply Scheme for installation of FHTC under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000499/2024-2025 | 43/RD/PHE | 03/01/2025 | 17/02/2025 | HAQUE CONSTRUCTION | 40.57 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | SM/11726 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000039/2023-2024 | 1538/RD/PHE | 24/05/2023 | 10/07/2024 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.14 | 0 | 0 | 100
Total | [13 empty] | 669.01 | 0 | 0