## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-II Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000161/2022-2023 | 2021/RD/PHE | 17/11/2022 | 15/02/2023 | BHOLA PAUL | 64.54 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000967/2022-2023 | 2953/MLMD | 28/12/2022 | 28/03/2023 | BISWAS SUPPLIERS. | 10.94 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site and(3.6x3.0) at 2nd Tubewell Site of Hemtabad Zone-II Water Supply Schemes Augmentation under Hemtabad Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000263/2022-2023 | 389/RD/PHE | 07/02/2023 | 24/03/2023 | M/S SANJIB BHATTACHARJEE SANJIB.RNJ@GMAIL.COM | 11.8 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000372/2022-2023 | 729/RD/PHE | 15/03/2023 | 14/03/2024 | SOVAN KUMAR ROY | 143.15 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Hemtabad Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I |  | ORD/000618/2023-2024 | 2657/MLMD | 10/08/2023 | 06/11/2028 | MAA BHABOTARINE ENTERPRISE. | 9.02 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. II (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001059/2022-2023 | 4003083063 | 13/02/2023 | 20/02/2023 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. I (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001060/2022-2023 | 4003083051 | 13/02/2023 | 20/02/2023 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1953/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 143.46 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Augmentation work of HEMTABAD ZONE-II Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000101/2022-2023 | 1548/RD/PHE | 26/08/2022 | 24/11/2022 | UTTAM SAHA | 425.89 | 0 | 0 | 52
10 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000968/2022-2023 | 245/MLMD | 24/02/2023 | 25/05/2023 | DAS CONSTRUCTION | 11.06 | 0 | 0 | 100
11 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I | Junior Engineer-07 | ORD/000139/2023-2024 | 1664/MLMD | 28/06/2023 | 26/09/2023 | PABITRA MANDAL | 11.51 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hemtabad, Zone-II, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02465/2023-2024 | BP-2023-24-414 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 0
Total | [13 empty] | 837.1 | 0 | 0