## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-II Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000161/2022-2023 | 2021/RD/PHE | 17/11/2022 | 15/02/2023 | BHOLA PAUL | 64.54 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000967/2022-2023 | 2953/MLMD | 28/12/2022 | 28/03/2023 | BISWAS SUPPLIERS. | 10.94 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site and(3.6x3.0) at 2nd Tubewell Site of Hemtabad Zone-II Water Supply Schemes Augmentation under Hemtabad Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000263/2022-2023 | 389/RD/PHE | 07/02/2023 | 24/03/2023 | M/S SANJIB BHATTACHARJEE SANJIB.RNJ@GMAIL.COM | 11.8 | 11.38 | 96.39 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000372/2022-2023 | 729/RD/PHE | 15/03/2023 | 14/03/2024 | SOVAN KUMAR ROY | 143.15 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Hemtabad Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I |  | ORD/000618/2023-2024 | 2657/MLMD | 10/08/2023 | 06/11/2028 | MAA BHABOTARINE ENTERPRISE. | 9.02 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. II (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001059/2022-2023 | 4003083063 | 13/02/2023 | 20/02/2023 | W.B.S.E.D.C.LTD | 0.54 | 0.54 | 100 | 0
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. I (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001060/2022-2023 | 4003083051 | 13/02/2023 | 20/02/2023 | W.B.S.E.D.C.LTD | 0.65 | 0.65 | 100 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1953/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 143.46 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Augmentation work of HEMTABAD ZONE-II Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000101/2022-2023 | 1548/RD/PHE | 26/08/2022 | 24/11/2022 | UTTAM SAHA | 425.89 | 144.03 | 33.82 | 52
10 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000968/2022-2023 | 245/MLMD | 24/02/2023 | 25/05/2023 | DAS CONSTRUCTION | 11.06 | 10.89 | 98.46 | 100
11 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I | Junior Engineer-07 | ORD/000139/2023-2024 | 1664/MLMD | 28/06/2023 | 26/09/2023 | PABITRA MANDAL | 11.51 | 11.42 | 99.22 | 100
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hemtabad, Zone-II, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02465/2023-2024 | BP-2023-24-414 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.18 | 3.61 | 100
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation of Hemtabad Zone-II PWSS at Hemtabad Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000157/2024-2025 | 2889/RD/PHE | 25/09/2024 | 09/11/2024 | M/S SANJIB BHATTACHARJEE | 24.46 | 0 | 0 | 100
Total | [13 empty] | 866.55 | 179.09 | 20.67