## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Repairing of Pump House at 3rd Tubewell site in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000252/2022-2023 | 380/RD/PHE | 07/02/2023 | 24/03/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.06 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of RAGHABPUR Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000210/2022-2023 | 79/RD/PHE | 17/01/2023 | 14/09/2023 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 86.06 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Raghabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011648) | Assistant Engineer - I |  | ORD/000612/2023-2024 | 2654/MLMD | 10/08/2023 | 06/11/2028 | DAS CONSTRUCTION | 10.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001052/2022-2023 | 253/MLMD | 24/02/2023 | 25/05/2023 | S.P. ENTERPRISE (KOLKATA) | 10.45 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001160/2022-2023 | 4003118806 | 26/03/2023 | 02/04/2023 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Pump House at 3rd tubewell Site (3.60mx3.00m ) Raghabpur Piped Water Supply Scheme in connection with Augmentation of Raghabpur PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD |  | ORD/000041/2023-2024 | 1540/RD/PHE | 24/05/2023 | 23/07/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 4.09 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001940/2023-2024 | 4003266667 | 23/11/2023 | 21/02/2024 | W.B.S.E.D.C.LTD | 6.4 | 0 | 0 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1943/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 20.88 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | FHTC (Functional Household Tap Connection) for Raghabpur Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000162/2022-2023 | 2022/RD/PHE | 17/11/2022 | 15/02/2023 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 53.39 | 0 | 0 | 70
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Raghabpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000335/2024-2025 | 3291/RD/PHE | 20/11/2024 | 04/01/2025 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 39.82 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Laying additional pipe line with FHTC for Augmentation Of Raghabpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000466/2024-2025 | 3784/RD/PHE | 19/12/2024 | 02/02/2025 | BIKASH KAR | 26.17 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Augmentation of RAGHABPUR Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000103/2022-2023 | 1550/RD/PHE | 26/08/2022 | 24/11/2022 | DIPESH BHOWMIK | 144.6 | 0 | 0 | 100
13 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001051/2022-2023 | 0252/MLMD | 24/02/2023 | 25/05/2023 | DEB CONSTRUCTION. | 10.36 | 0 | 0 | 100
14 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001053/2022-2023 | 254/MLMD | 24/02/2023 | 25/05/2023 | FUTURE | 10.55 | 0 | 0 | 100
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000238/2022-2023 | 371/RD/PHE | 07/02/2023 | 24/03/2023 | D. K. ASSOCIATES BISWAJITKAR9434@GMAIL.COM | 4.96 | 0 | 0 | 100
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Repairing of Pump House at 2nd Tubewell site in connection with Augmentation of RAGHABPUR Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000239/2022-2023 | 372/RD/PHE | 07/02/2023 | 24/03/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.02 | 0 | 0 | 100
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Raghabpur Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000352/2025-2026 | 2498/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0 | 0
Total | [13 empty] | 462.5 | 0 | 0