## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 2264/RD/PHE | 23/12/2022 | 23/12/2022 | Resource Division | 119.05 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Repairing of Pump House at 2nd tube well site in connection with Augmentation of Karandighi Zone -II Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000237/2022-2023 | 370/RD/PHE | 07/02/2023 | 24/03/2023 | ALI ENTERPRISE ALIENTERPRISE.HEM@GMAIL.COM | 2.1 | 1.71 | 81.19 | 100
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Karandighi, Zone-II, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001159/2022-2023 | 4003118849 | 26/03/2023 | 02/04/2023 | W.B.S.E.D.C.LTD | 0.55 | 0.55 | 100 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/001359/2022-2023 | 271/MLMD | 24/02/2023 | 25/04/2023 | RAMCHANDRA BASAK | 0.29 | 0.28 | 99.44 | 100
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-I ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/001360/2022-2023 | 271/MLMD. | 24/02/2023 | 25/04/2023 | RAMCHANDRA BASAK | 0.51 | 0.51 | 100 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well under Augmentation Of Karandighi Zone-II PWSS at Karandighi Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000333/2024-2025 | 3289/RD/PHE | 20/11/2024 | 04/01/2025 | KARTICK BISWAS | 36.07 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of KARANDIGHI(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000211/2022-2023 | 80/RD/PHE | 17/01/2023 | 14/09/2023 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 86.13 | 84.38 | 97.97 | 1
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000236/2022-2023 | 369/RD/PHE | 07/02/2023 | 24/03/2023 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 5.03 | 5.02 | 99.71 | 100
9 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001047/2022-2023 | 248/MLMD | 24/02/2023 | 25/05/2023 | MANAS KUMAR SAHA | 10.46 | 10.34 | 98.8 | 100
10 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001048/2022-2023 | 249/MLMD | 24/02/2023 | 25/05/2023 | SOVON KUMAR DAS. | 10.55 | 10.37 | 98.24 | 100
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | FHTC (Functional Household Tap Connection) for Karandighi Zone-II Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000157/2022-2023 | 2017/RD/PHE | 17/11/2022 | 07/08/2024 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.82 | 0 | 0 | 60
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Augmentation of KARANDIGHI(Zone-II)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal.(2nd Call). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000151/2022-2023 | 2047/RD/PHE | 21/11/2022 | 31/03/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 154.85 | 98.79 | 63.8 | 70
13 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Karandighi Water Supply Scheme, ( Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011647) | Assistant Engineer - I | Junior Engineer-02 | ORD/000207/2023-2024 | 2130/MLMD | 07/07/2023 | 03/10/2028 | M/S. KUNDU CONSTRACTION | 6.97 | 0 | 0 | 80
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Providing FHTC in connection with augmentation of Karandighi Zone-II Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000503/2024-2025 | 48/RD/PHE | 03/01/2025 | 17/02/2025 | AJIT PRAMANIK | 15.76 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Trial Run For Karandighi Zone-II PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000708/2024-2025 | 546/RD/PHE | 12/02/2025 | 13/05/2025 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11794 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-II Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000353/2025-2026 | 2499/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 29.58 | 0 | 0 | 0
Total | [13 empty] | 540.41 | 211.95 | 39.22