## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba (Itahar) Water Supply Scheme Scheme at Itahar Block under Raiganj Division P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000261/2022-2023 | 387/RD/PHE | 07/02/2023 | 24/03/2023 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 3.48 | 3.42 | 98.14 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA ITAHAR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001114/2022-2023 | 424/MLMD | 14/03/2023 | 12/06/2023 | M.S. ENTERPRISE | 11.56 | 11.54 | 99.86 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA ITAHAR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001106/2022-2023 | 425/MLMD | 14/03/2023 | 12/06/2023 | T.N. BANERJEE | 11.25 | 11.24 | 99.91 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1951/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 50.19 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Hiring of vehicle for inspection and monitoring of Augmentation work of Kasba(Itahar) under JJM under Raiganj sub-division of Raiganj Division, PHE Dte. for the period from 24.11.2022 to 05.12.2022. |  |  | BILL/00228/2023-2024 | BP-2023-24-76 | 19/07/2023 | 19/07/2023 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | FHTC (Functional Household Tap Connection) for Kasba (Itahar) Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000159/2022-2023 | 2019/RD/PHE | 17/11/2022 | 15/02/2023 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 60.76 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Kasba (Itahar) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011409) | Assistant Engineer - I | Junior Engineer-02 | ORD/000763/2023-2024 | 2806/MLMD | 17/08/2023 | 13/11/2028 | THE BUSINESS ENGINEERS INDIA | 6.77 | 5.75 | 84.98 | 85
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Augmentation work of KASBA(Itahar) and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000096/2022-2023 | 1543/RD/PHE | 26/08/2022 | 13/11/2024 | SANYAL ENTERPRISE | 300.01 | 211.01 | 70.33 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000402/2024-2025 | 3571/RD/PHE | 05/12/2024 | 19/01/2025 | SAHA CONSTRUCTION | 15.15 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | SM/11796 | Augmentation | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000419/2024-2025 | 3572/RD/PHE | 05/12/2024 | 05/03/2025 | SANTI TRADERS | 15.15 | 0 | 0 | 0
Total | [13 empty] | 474.43 | 242.96 | 51.21