## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Augmentation work of KASBA(NM) Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000097/2022-2023 | 1544/RD/PHE | 26/08/2022 | 24/11/2022 | AJIT PARMANIK | 212.07 | 176.01 | 83 | 95
2 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 1974/RD/PHE | 08/11/2022 | 08/11/2022 | Resource Division | 36.35 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000269/2022-2023 | 433/RD/PHE | 10/02/2023 | 27/03/2023 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 3.24 | 3.13 | 96.51 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001110/2022-2023 | 426/MLMD | 14/03/2023 | 12/06/2023 | HANNAN BUILDERS PVT. LTD. | 10.8 | 10.72 | 99.2 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Construction of Over Head Reservoir(Capacity-450 Cum) of KASBA(NM) Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000368/2022-2023 | 725/RD/PHE | 15/03/2023 | 28/02/2026 | CHAKRABORTY CONSTRUCTION | 158.66 | 13.7 | 8.63 | 40
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | FHTC (Functional Household Tap Connection) for Kasba(NM) Water Supply Scheme [Augmentation Scheme]in Raiganj Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000402/2022-2023 | 757/RD/PHE | 17/03/2023 | 26/05/2025 | BHOLA PAUL | 92.67 | 51.26 | 55.31 | 55
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Kasba-NM PWSS | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000283/2023-2024 | 2362/RD/PHE | 11/08/2023 | 10/10/2023 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 5.02 | 3.27 | 65.13 | 92
8 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001111/2022-2023 | 427/MLMD | 14/03/2023 | 12/06/2023 | MERCURY ENGINEERING COMPANY. | 10.44 | 10.36 | 99.22 | 100
9 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Kasba (NM) PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000007/2023-2024 | 4003132613 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.54 | 0.54 | 100 | 0
10 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001112/2022-2023 | 428/MLMD | 14/03/2023 | 12/06/2023 | KUNDU CONSTRUCTION. | 10.97 | 10.9 | 99.37 | 100
11 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Kasba (NM), Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001925/2023-2024 | 100000094175 | 30/11/2023 | 28/02/2024 | W.B.S.E.D.C.LTD | 1.17 | 1.17 | 100 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Construction of Boundary Wall With Gate at 2nd and 3rd Tube-Well Site under Augmentation Kasba NM PWSS at Raiganj Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000155/2024-2025 | 2887/RD/PHE | 25/09/2024 | 09/11/2024 | BHOLA PAUL | 11.13 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Additional Pipe Line (UPVC) For Providing FHTC at Kasba(NM) PWSS at Raiganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000032/2024-2025 | 1693/RD/PHE | 10/06/2024 | 25/07/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 10.68 | 0 | 0 | 100
14 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
15 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kasba NM PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000656/2024-2025 | 417/RD/PHE | 29/01/2025 | 15/03/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.32 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | SM/11797 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000282/2025-2026 | 1801/RD/PHE | 24/06/2025 | 21/12/2025 | AJIT PRAMANIK | 18.73 | 0 | 0 | 0
Total | [13 empty] | 598.81 | 281.05 | 46.94