## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte | Assistant Engineer - I | Junior Engineer-07 | ORD/000017/2023-2024 | 781/MLMD | 27/04/2023 | 26/07/2023 | NEOGI ENTERPRISE. | 10.38 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site of Sariabad Augmentation Water Supply Schemes under Raiganj Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000262/2022-2023 | 388/RD/PHE | 07/02/2023 | 24/03/2023 | SANTOSI ENTERPRISE AMIT.RAIGANJ@GMAIL.COM | 5.79 | 0 | 0 | 100
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W.No. I of Sariabad pwss, Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001133/2022-2023 | 4003055164 | 28/12/2022 | 04/01/2023 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000107/2023-2024 | 1115/MLMD | 23/06/2023 | 21/09/2023 | ANIMA ENTERPRISE | 10.55 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1949/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 33.5 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Augmentation of SARIABAD Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000102/2022-2023 | 1549/RD/PHE | 26/08/2022 | 13/03/2025 | TAPAN KUMAR DUTTA | 152.36 | 0 | 0 | 90
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000018/2023-2024 | 782/MLMD | 27/04/2023 | 01/07/2025 | M/S SAJAHAN CHOWDHURY | 10.38 | 0 | 0 | 81
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sariyabad PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000437/2024-2025 | 3749/RD/PHED | 18/12/2024 | 01/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 37.92 | 0 | 0 | 75
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation of Sariabad PWSS at Raiganj Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000156/2024-2025 | 2888/RD/PHE | 25/09/2024 | 09/11/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 37.18 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sariabad Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000272/2025-2026 | 1659/RD/PHE | 23/06/2025 | 20/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.57 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | FHTC (Functional Household Tap Connection) for Sariabad Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000171/2022-2023 | 2031/RD/PHE | 17/11/2022 | 04/06/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.4 | 0 | 0 | 67
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Repairing of Pump House of 2nd Tube Well and 3rd Tube Well Site of Sariabad Augmentation Water Supply Scheme at Raiganj Block under Raiganj Division P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000265/2022-2023 | 401/RD/PHE | 08/02/2023 | 03/05/2024 | LAXMI CONSTRUCTION NAMEDUTTA@GMAIL.COM | 3.31 | 0 | 0 | 80
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11798 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of SARIABAD Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000328/2022-2023 | 657/RD/PHE | 03/03/2023 | 21/01/2025 | VISCOUS ENGINEERS PVT. LTD. | 84.86 | 0 | 0 | 82
Total | [13 empty] | 460.77 | 0 | 0