## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-I) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001050/2022-2023 | 251/MLMD | 24/02/2023 | 25/05/2023 | H.K. DAS & CO. | 11.46 | 11.37 | 99.21 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Hemtabad Water Supply Scheme, ( Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011647) |  |  | ORD/001817/2023-2024 | 3701/MLMD | 29/11/2023 | 27/11/2028 | AMITAVA CHAKRABORTY | 6.85 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-I) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001049/2022-2023 | 250/MLMD | 24/02/2023 | 25/05/2023 | AHALYA ENGINEERING WORKS | 11.51 | 11.47 | 99.59 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Repairing of Pump house of Head Works and 2nd Tube Well Site in connection with Augmentation of Hemtabad Zone-I Water Supply Scheme at Hemtabad block under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000264/2022-2023 | 400/RD/PHE | 08/02/2023 | 25/03/2023 | M/S SARKAR ENTERPRISE (UDAYPUR) SARKARTAPATI.UDI@GMAIL.COM | 2.98 | 2.94 | 98.51 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1952/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 91.08 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1518/RD/PHE | 23/05/2023 | 23/05/2023 | Resource Division | 2.02 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Augmentation work of HEMTABAD ZONE-I Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000119/2022-2023 | 1754/RD/PHE | 15/09/2022 | 14/12/2022 | M/S LOKENATH CONSTRUCTION | 501.39 | 151.74 | 30.26 | 90
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Construction of boundary wall & toilet block of Augmentation of Hemtabad Zone-I PWSS at 2nd tube well site at Hemtabad block under Raiganj Division PHE Dte., Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000413/2023-2024 | 2785/RD/PHE | 10/10/2023 | 24/12/2023 | M/S SARKAR ENTERPRISE UDAYPUR | 5.05 | 4.33 | 85.8 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-I Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000168/2022-2023 | 2028/RD/PHE | 17/11/2022 | 18/03/2025 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 72.5 | 34.31 | 47.33 | 60
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11799 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000375/2022-2023 | 730/RD/PHE | 15/03/2023 | 26/05/2024 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 143.13 | 92.24 | 64.44 | 40
Total | [13 empty] | 847.97 | 308.4 | 36.37