## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 1973/RD/PHE | 08/11/2022 | 08/11/2022 | Resource Division | 67.7 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | FHTC (Functional Household Tap Connection) for Panjipara Zone-II Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000165/2022-2023 | 2025/RD/PHE | 17/11/2022 | 15/02/2023 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 78.25 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Panjipara, Zone-II, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000088/2023-2024 | 4003160488 | 19/05/2023 | 18/05/2024 | W.B.S.E.D.C.LTD | 7.27 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Panjipara (Zone- II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011660) |  |  | ORD/002032/2023-2024 | 4769/MLMD | 29/12/2023 | 27/03/2029 | THE BUSINESS ENGINEERS INDIA | 6.76 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000229/2022-2023 | 362/RD/PHE | 07/02/2023 | 24/03/2023 | PULAK TALUKDAR PULAK.RNJ@GMAIL.COM | 5 | 0 | 0 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Panjipara Zone-II piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000230/2022-2023 | 363/RD/PHE | 07/02/2023 | 24/03/2023 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.5 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Augmentation of PANJIPARA(Zone-II)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000117/2022-2023 | 1669/RD/PHE | 05/09/2022 | 04/12/2022 | UTTAM SAHA | 207.19 | 0 | 0 | 80
8 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-II) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001093/2022-2023 | 264/MLMD | 24/02/2023 | 25/05/2023 | MAA BHABOTARINE ENTERPRISE. | 11.47 | 0 | 0 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Construction Of Approach Road in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpokhur- I Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000456/2024-2025 | 3774/RD/PHE | 19/12/2024 | 19/03/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.35 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Construction Of Boundary Wall With Gate at 2nd Tube-Well Site in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000341/2024-2025 | 3311/RD/PHE | 20/11/2024 | 20/12/2024 | MR CONSTRUCTION | 8.86 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Trial Run For Panjipara Zone-II PWSS under Goalpukhur-I Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000723/2024-2025 | 555/RD/PHE | 12/02/2025 | 13/05/2025 | APEX ENTERPRISES | 0.88 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panjipara Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000305/2025-2026 | 1969/RD/PHE | 02/07/2025 | 29/12/2025 | AJIT PRAMANIK | 32.35 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11801 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000378/2022-2023 | 733/RD/PHE | 15/03/2023 | 30/11/2024 | M/S ELITE CONSTRUCTION | 143.09 | 0 | 0 | 100
Total | [13 empty] | 583.47 | 0 | 0