## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Ramganj Water Supply Scheme (Zone-II) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001074/2022-2023 | 259/MLMD | 24/02/2023 | 25/05/2023 | DEVI ENTERPRISE... | 11.53 | 10.15 | 88.02 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of RAMGANJ(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000376/2022-2023 | 731/RD/PHE | 15/03/2023 | 14/03/2024 | SOVAN KUMAR ROY | 143.15 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Ramganj, Zone-II, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000033/2023-2024 | 4003120505 | 28/04/2023 | 27/07/2023 | W.B.S.E.D.C.LTD | 9.99 | 9.99 | 100 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Ramganj, Zone-II, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000034/2023-2024 | 4003120516 | 28/04/2023 | 27/07/2023 | W.B.S.E.D.C.LTD | 13.59 | 13.59 | 100 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Laying of Additional Pipe line for Ramganj Zone-II Piped water Supply Scheme in connection with Augmentation of Ramganj Zone-II PWSS under Raiganj Division P.H.E. Dte in the District of Uttar Dinajpur. | Assistant Engineer ISD |  | ORD/000044/2023-2024 | 1543/RD/PHE | 24/05/2023 | 23/06/2023 | UJJWAL DAS | 7.59 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000235/2022-2023 | 368/RD/PHE | 07/02/2023 | 24/03/2023 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 5.02 | 5.01 | 99.91 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m)in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000251/2022-2023 | 379/RD/PHE | 07/02/2023 | 24/03/2023 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 4.1 | 4.09 | 99.86 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1946/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 55.2 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Ramganj Water Supply Scheme, (Zone-II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011644) | Assistant Engineer - I |  | ORD/000615/2023-2024 | 2655/MLMD | 10/08/2023 | 06/11/2028 | DAS CONSTRUCTION | 10.54 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Augmentation of RAMGANJ(Zone-II)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000105/2022-2023 | 1552/RD/PHE | 26/08/2022 | 21/11/2024 | UJJWAL DAS | 177.43 | 144.88 | 81.65 | 98
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | FHTC (Functional Household Tap Connection) for Ramganj Zone-II Water Supply Scheme [Augmentation Scheme] in Islampur Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000158/2022-2023 | 2018/RD/PHE | 17/11/2022 | 15/02/2023 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 56.88 | 53.98 | 94.89 | 38
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Supply, Installation & Commissioning of electro-mechanical accessories and other allied works at Augmentation of Ramganj Zone-II (PH-I) W/S Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/002494/2023-2024 | 837/MLMD | 19/02/2024 | 05/03/2024 | MAA BHABOTARINE ENTERPRISE | 1.45 | 1.34 | 92.4 | 100
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Providing FHTC in connection with augmentation of Ramganj Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000505/2024-2025 | 50/RD/PHE | 03/01/2025 | 17/02/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 29.19 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Restoration of damaged pipeline with some ancillary works at different mouzas under Ramganj Z-II PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000346/2024-2025 | 3299/RD/PHE | 20/11/2024 | 04/04/2025 | UJJWAL DAS | 21.68 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Balance Distribution System of Laying Pipeline with Construction of Boundary Wall with Gate at Head Work Site & 2nd Tube-Well Site under RAMGANJ Zone-II PWSS(Augmentation) at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000567/2023-2024 | 739/RD/PHE | 12/03/2024 | 12/09/2025 | SOVAN KUMAR ROY | 25.87 | 0 | 0 | 95
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0.36 | 7.53 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Trial Run For Ramganj Zone-II PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000707/2024-2025 | 545/RD/PHE | 12/02/2025 | 13/05/2025 | UJJWAL DAS | 0.88 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Ramganj Water Supply Scheme (Zone-II) TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001405/2022-2023 | 262/MLMD | 24/02/2023 | 25/05/2023 | DILIP MAHATO. | 11.45 | 0 | 0 | 0
19 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-II Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000356/2025-2026 | 2502/RD/PHE | 12/09/2025 | 11/03/2026 | JAL PRAVAHIKA PRIVATE LIMITED | 32.32 | 0 | 0 | 0
20 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under Augmentation of Ramganj Zone-II PWSS at Islampur Block under Raiganj Division, PHE dte. (3rd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000243/2025-2026 | 1463/RD/PHE | 04/06/2025 | 04/07/2025 | ZAREEN ENTERPRISE | 14.6 | 0 | 0 | 0
21 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11802 | Augmentation | Sinking of Rigbored Tube-Well (300mm x 200mm big dia) at Ramganj(Zone-II)Water Supply Scheme in connection with 4 nos. replacement tube-well at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte., Govt. of West Bengal. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000254/2025-2026 | 2043/RD/PHE | 09/07/2025 | 05/01/2026 | UJJWAL DAS | 15.26 | 0 | 0 | 100
Total | [13 empty] | 652.52 | 243.39 | 37.3