## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory personnel for 02(two) Sub-district Laboratories for water quality monitoring & Surveillance of Spot Source and piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [Part-A] and Day to Day to washing cleaning of all laboratory instruments, Laboratory room including meeting room and other inside area of Laboratory etc. of 02(two) Sub-District Laboratories at Itahar & Goalpokhar (Part B) under Raiganj Division, PHE Dte 01 Month (01.01.2022 to 31.01.2022) | Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000808/2021-2022 | 2432/RD/PHE | 31/12/2021 | 31/01/2022 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.57 | 0.57 | 100 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) Nos. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for Hemtabad Sub-District Laboratories under Raiganj Division, P.H.E. Dte. (Period from 01.07.2022 to 31.03.2023) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000068/2022-2023 | 1343/RD/PHE | 08/07/2022 | 04/04/2023 | DULAL MAJUMDER | 4.42 | 4.25 | 96.2 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Itahar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 12(Twelve) Months (01.02.2022 to 31.01.2023) | Assistant Engineer RSD |  | ORD/000721/2021-2022 | 313/RD/PHE | 31/01/2022 | 31/01/2023 | DULAL MAJUMDER | 3.74 | 3.73 | 99.7 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) Nos.Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for Islampur Sub-District Laboratories under Raiganj Division, P.H.E. Dte. (Period from 01.07.2022 to 31.03.2023) | Assistant Engineer ISD |  | ORD/000069/2022-2023 | 1344/RD/PHE | 08/07/2022 | 04/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 4.42 | 4.42 | 100 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Goalpokhar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 12(Twelve) Months (01.02.2022 to 31.01.2023) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000722/2021-2022 | 314/RD/PHE | 31/01/2022 | 31/01/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 3.74 | 3.74 | 100 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for District Laboratory for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room including meeting room and other inside area of Laboratory etc. of District Laboratory at Karnajora[Part-B] under Raiganj Division, P.H.E. Dte. [(For the period from 16.01.2022 to 15.01.2023) 12(twelve) Months.] | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000479/2021-2022 | 82/RD/PHE | 14/01/2022 | 14/01/2023 | DULAL MAJUMDER | 8.47 | 7.41 | 87.51 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div | SM/11803 | Support-WQMSP | Continuation Order for Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Goalpokhar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 59(Fifty Nine) Days (01.02.2023 to 31.03.2023) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000337/2022-2023 | 283/RD/PHE | 31/01/2023 | 31/03/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.62 | 0.62 | 100 | 100
Total | [13 empty] | 25.96 | 24.73 | 95.24