## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in WBCADC Kaliyaganj Project SD Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000061/2021-2022 | 1784/RD/PHE | 10/09/2021 | 25/09/2021 | DULAL MAJUMDER | 4.96 | 4.96 | 100 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Goalpokhar-I Sub- District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000062/2021-2022 | 1785/RD/PHE | 10/09/2021 | 25/09/2021 | DULAL MAJUMDER | 4.84 | 4.84 | 100 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | DEPLYOMENT OF LABORATORY PERSONNEL FOR 02 DISTRICT LABORATORIES FOR WQMSP AND PWSS AND DAY TO DAY WASHING CLEANING OF ALL LABORATORY OF DISTRICT LABORATORIES | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000791/2021-2022 | 1162/ RD | 01/06/2021 | 28/11/2021 | DULAL MAJUMDER | 4.16 | 1.23 | 29.58 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Prashika RDO Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000060/2021-2022 | 1783/RD/PHE | 10/09/2021 | 25/09/2021 | DULAL MAJUMDER | 4.72 | 4.72 | 100 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | LABORATORY BILL | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000762/2021-2022 | 1162/RD | 01/06/2021 | 28/11/2021 | DULAL MAJUMDER | 4.16 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Requirement of Consumables Chemicals for District Laboratory under Raiganj Division, P.H.E. Dte. (Part-A) | Assistant Engineer RSD |  | ORD/000334/2022-2023 | 709/RD/PHE | 13/03/2023 | 20/03/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.96 | 0.96 | 100 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Requirement of Consumables Chemicals for District Laboratory under Raiganj Division, P.H.E. Dte. (Part-B) | Assistant Engineer RSD |  | ORD/000335/2022-2023 | 710/RD/PHE | 13/03/2023 | 20/03/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.95 | 0.95 | 100 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for District Laboratory Karnajora under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000211/2024-2025 | 2704/RD/PHE | 09/09/2024 | 24/09/2024 | DULAL MAJUMDER | 0.98 | 0 | 0 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Islampur Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000212/2024-2025 | 2707/RD/PHE | 09/09/2024 | 24/09/2024 | DULAL MAJUMDER | 0.95 | 0 | 0 | 100
10 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Itahar Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000213/2024-2025 | 2708/RD/PHE | 09/09/2024 | 24/09/2024 | DULAL MAJUMDER | 0.92 | 0 | 0 | 100
11 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Goalpokhar Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000214/2024-2025 | 2709/RD/PHE | 09/09/2024 | 24/09/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. | SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Hemtabad Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000215/2024-2025 | 2710/RD/PHE | 09/09/2024 | 24/09/2024 | DULAL MAJUMDER | 0.7 | 0 | 0 | 100
Total | [13 empty] | 29.14 | 17.65 | 60.56