## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Implementation of TENAHARI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000155/2022-2023 | 1994/RD/PHE | 14/11/2022 | 14/11/2023 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 260.7 | 236.25 | 90.62 | 80
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 2123/RD/PHE | 03/12/2022 | 03/12/2022 | Resource Division | 31.4 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Tenahari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011957) | Assistant Engineer - I | Junior Engineer-07 | ORD/000116/2023-2024 | 1135/MLMD | 26/06/2023 | 24/10/2023 | DEBAPRIYA SAHA | 27.11 | 22.5 | 83 | 86
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Tenahari PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000002/2023-2024 | 4003133018 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.63 | 0.63 | 100 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Tenahari PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000001/2023-2024 | 4003133029 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.74 | 0.74 | 100 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Construction of Pump House & Boundary Wall at Tenahari Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. (Pump House at Head Work, 2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000260/2022-2023 | 386/RD/PHE | 08/02/2023 | 28/02/2024 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 36.15 | 32.23 | 89.17 | 100
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.01.2023 to 15.02.2023. |  |  | BILL/00944/2023-2024 | BP-2023-24-213 | 07/12/2023 | 07/12/2023 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Tenahari PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000431/2024-2025 | 3744/RD/PHE | 18/12/2024 | 02/05/2025 | M/S MAA TARA CONSTRUCTION | 26.62 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.3 | 5.98 | 100
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Trial Run For Tenahari PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000704/2024-2025 | 543/RD/PHE | 12/02/2025 | 13/05/2025 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 28.03.2024 and 01.04.2024 to 04.04.2024. |  |  | BILL/00588/2024-2025 | BP-2024-25-299 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 08.04.2024 to 09.04.2024 and 12.04.2024. |  |  | BILL/00589/2024-2025 | BP-2024-25-300 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.03 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 04.03.2024 to 07.03.2024. |  |  | BILL/00585/2024-2025 | BP-2024-25-297 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.05 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Raiganj | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 18.03.2024 to 22.03.2024. |  |  | BILL/00587/2024-2025 | BP-2024-25-298 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.05 | 0 | 0 | 0
Total | [13 empty] | 389.81 | 292.66 | 75.08