## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 2125/RD/PHE | 03/12/2022 | 03/12/2022 | Resource Division | 26.44 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PASCHIM GOALGAON PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000424/2023-2024 | 4003196193 | 27/07/2023 | 25/10/2023 | W.B.S.E.D.C.LTD | 6.65 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PASCHIM GOALGAON PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000425/2023-2024 | 4003196200 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.27 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Paschim Goalgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011936) | Assistant Engineer - I | Junior Engineer-07 | ORD/000174/2023-2024 | 2095/MLMD | 04/07/2023 | 31/12/2023 | SRI KRISHNA NIRMAN | 24.03 | 0 | 0 | 88
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | DI Pipe Carrying RCC Structure Through River of Paschim Goalgaon PWSS(New Scheme) at Raiganj Block under Raiganj Division P.H.E. Dte., Uttar Dinajpur.(Phase-I) | Assistant Engineer RSD |  | ORD/000147/2024-2025 | 3015/RD/PHE | 03/10/2024 | 17/11/2024 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 29.02 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Implementation of PASCHIM GOALGAON and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000154/2022-2023 | 1993/RD/PHE | 14/11/2022 | 01/01/2026 | M/S LOKENATH CONSTRUCTION | 487.48 | 0 | 0 | 60
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Construction of Pump House & Boundary Wall at Paschim Goalgaon Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000257/2022-2023 | 383/RD/PHE | 07/02/2023 | 31/12/2023 | HERO CONSTRUCTION HEROCONST.RNJ@GMAIL.COM | 35.61 | 0 | 0 | 67
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Goalgaon PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000480/2024-2025 | 13/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.4 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 | New | Trial Run For Paschim Goalgaon PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000690/2024-2025 | 535/RD/PHE | 12/02/2025 | 13/05/2025 | M/S RATAN SARKAR & SON | 0.87 | 0 | 0 | 0
Total | [13 empty] | 656.77 | 0 | 0