## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Kuliara Anantapur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001884/2023-2024 | 4003203670 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 8.31 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 521/RD/PHE | 20/02/2023 | 20/02/2023 | Resource Division | 33.03 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 521/RD/PHE | 20/02/2023 | 20/02/2023 | Resource Division | 32.76 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KULIARA ANANTAPUR PWSS ,Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02584/2023-2024 | BP-2023-24-465 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Modified Quotation Charge at TW No- II of Kuliara Anantapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00237/2024-2025 | BP-2024-25-98 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 7.84 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Implementation of KULIARA ANANTAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (2nd Call) | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000218/2022-2023 | 96/RD/PHE | 19/01/2023 | 01/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 369 | 0 | 0 | 45
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Construction of Pump House & Boundary Wall at Kuliara Anantapur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work, 2nd Tube Well and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000255/2022-2023 | 382/RD/PHE | 08/02/2023 | 30/03/2025 | M/S. BANGARAJ ASHOKLALRNJ@GMAIL.COM | 36.13 | 0 | 0 | 70
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Kuliara Anantapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011943) | Assistant Engineer - I | Junior Engineer-07 | ORD/001802/2023-2024 | 3689/MLMD | 29/11/2023 | 14/09/2025 | MANIK CHANDRA SAHA. | 25.33 | 0 | 0 | 78
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kuliara Anantapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000438/2024-2025 | 3750/RD/PHED | 18/12/2024 | 02/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.59 | 0 | 0 | 0
Total | [13 empty] | 553.45 | 0 | 0