## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Implementation of MALADKHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000309/2022-2023 | 555/RD/PHE | 23/02/2023 | 16/04/2026 | UTTAM SAHA | 685.62 | 302 | 44.05 | 53
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Making compound lighting arrangement with allied works at T/W no. I of Maladhanda Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011914) | Assistant Engineer - I | Junior Engineer-07 | ORD/000706/2023-2024 | 2236/MLMD | 12/07/2023 | 10/10/2023 | M/S. MAYUKH BHADURI | 2.64 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Rig bored Tubewell at MALADKHANDA PWSS in connection with Implementation of New Maladkhanda PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000411/2023-2024 | 2751/RD/PHE | 05/10/2023 | 25/10/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 26.26 | 25.26 | 96.2 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MALADKHANDA Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001794/2023-2024 | 3681/MLMD | 29/11/2023 | 11/03/2025 | M/S SABANA CONSTRUCTION | 12.11 | 10.38 | 85.72 | 85
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Maladkhanda PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001883/2023-2024 | 4003133003 | 16/04/2023 | 15/07/2023 | W.B.S.E.D.C.LTD | 0.84 | 0.84 | 100 | 100
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 572/RD/PHE | 23/02/2023 | 23/02/2023 | Resource Division | 120.41 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALADKHANDA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000462/2023-2024 | 570/RD/PHE | 05/03/2024 | 23/03/2025 | M/S REGAL BUILDERS | 22.57 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Supply, delivery, installation, commissioning and trial operation of electro-mechanical components of Maladkhanda Water Supply Scheme TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000050/2024-2025 | 1571/MLMD | 07/06/2024 | 16/02/2025 | M/S SAJAHAN CHOWDHURY | 12.95 | 10.25 | 79.21 | 100
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.08 | 1.61 | 100
10 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Maladkhanda, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03639/2023-2024 | BP-2023-24-623 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of Headwork Site & 2nd Tubewell Site and Road Restoration of Maladkhanda PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000409/2025-2026 | 2220/RD/PHE | 30/07/2025 | 27/11/2025 | AJIT PRAMANIK | 93.42 | 0 | 0 | 0
Total | [13 empty] | 987.53 | 348.82 | 35.32