## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Making compound lighting arrangement with allied works at T/W no. I of Maladhanda Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011914) | Assistant Engineer - I | Junior Engineer-07 | ORD/000706/2023-2024 | 2236/MLMD | 12/07/2023 | 10/10/2023 | M/S. MAYUKH BHADURI | 2.64 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Maladkhanda PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001883/2023-2024 | 4003133003 | 16/04/2023 | 15/07/2023 | W.B.S.E.D.C.LTD | 0.84 | 0.84 | 100 | 100
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 572/RD/PHE | 23/02/2023 | 23/02/2023 | Resource Division | 120.41 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Rig bored Tubewell at MALADKHANDA PWSS in connection with Implementation of New Maladkhanda PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000411/2023-2024 | 2751/RD/PHE | 05/10/2023 | 25/10/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 26.26 | 25.26 | 96.2 | 100
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Maladkhanda, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03639/2023-2024 | BP-2023-24-623 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Implementation of MALADKHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000309/2022-2023 | 555/RD/PHE | 23/02/2023 | 18/10/2025 | UTTAM SAHA | 685.62 | 302 | 44.05 | 53
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALADKHANDA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000462/2023-2024 | 570/RD/PHE | 05/03/2024 | 23/03/2025 | M/S REGAL BUILDERS | 22.57 | 0 | 0 | 100
Total | [13 empty] | 859.06 | 328.1 | 38.19