## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of BAMANGRAM ,Bamongola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000035/2023-2024 | 3004228400 | 26/04/2023 | 25/07/2023 | W.B.S.E.D.C.LTD | 6.31 | 6.31 | 100 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Making compound lighting arrangement with allied works at T/W no. I of Bamangram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011913) | Assistant Engineer - I | Junior Engineer-07 | ORD/000705/2023-2024 | 2235/MLMD | 18/07/2023 | 16/10/2023 | CHATTERJEE CONSTRUCTION | 2.64 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 573/RD/PHE | 23/02/2023 | 23/02/2023 | Resource Division | 36.39 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Rig bored Tubewell at BAMANGRAM PWSS in connection with Implementation of New Bamangram PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000410/2023-2024 | 2750/RD/PHE | 05/10/2023 | 25/10/2023 | BHOLA PAUL | 26.11 | 24.37 | 93.33 | 98
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAMANGRAM Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001785/2023-2024 | 3349/MLMD | 30/10/2023 | 28/01/2024 | DEY ENTERPRISE.. | 11.23 | 9.47 | 84.39 | 84
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Charge against shifting/Reorientation of 1 no 25 KVA DTR on Safety ground at Tubewell site-I of Bamangram water supply scheme under Birnagar CCC in the District of Uttar Dinajpur |  |  | BILL/02413/2024-2025 | BP-2024-25-567 | 29/10/2024 | 29/10/2024 | W.B.S.E.D.C.LTD | 1.34 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bamangram, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03637/2023-2024 | BP-2023-24-621 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 6.51 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bamangram, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03543/2023-2024 | BP-2023-24-570 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 4.61 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Implementation of BAMANGRAM and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000310/2022-2023 | 561/RD/PHE | 23/02/2023 | 01/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 525.45 | 271 | 51.57 | 4
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Balance distribution System of Laying Pipeline with Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAMANGRAM Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000465/2023-2024 | 573/RD/PHE | 05/03/2024 | 28/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.87 | 0 | 0 | 80
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bamangram PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000440/2024-2025 | 3752/RD/PHED | 18/12/2024 | 02/05/2025 | BHOLA PAUL | 91.18 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Trial Run For Bamongram PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000699/2024-2025 | 540/RD/PHE | 12/02/2025 | 13/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bamangram Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000271/2025-2026 | 1658/RD/PHE | 23/06/2025 | 20/12/2025 | AJIT PRAMANIK | 32.35 | 0 | 0 | 0
Total | [13 empty] | 767.85 | 311.15 | 40.52