## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Cheramoti PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000003/2023-2024 | 4003132796 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Cheramoti PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000004/2023-2024 | 4003132810 | 12/04/2023 | 27/04/2023 | W.B.S.E.D.C.LTD | 0.49 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Continuation work- Hiring of Inspection Vehicle (Diesel Driven) for official use of Executive Engineer for the office of the Executive Engineer under Malda Mechanical Division, PHED. | Assistant Engineer - II | Junior Engineer-04 | ORD/001149/2022-2023 | 2965/MLMD | 28/12/2022 | 28/04/2023 | NITAI PANDEY | 0.72 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Claim for purchase of fuel for hiring of inspection for different site visit use for Executive Engineer-,Under Mechanical Division, P.H.E. Dte | Assistant Engineer - II | Junior Engineer-04 | ORD/001365/2022-2023 | 2965/MLMD. | 28/12/2022 | 27/04/2023 | NITAI PANDEY | 0.48 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 1954/RD/PHE | 04/11/2022 | 04/11/2022 | Resource Division | 16.22 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Implementation of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000116/2022-2023 | 1668/RD/PHE | 05/09/2022 | 01/01/2026 | SANYAL ENTERPRISE | 158.77 | 0 | 0 | 99
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Additional Pipe Line For Providing FHTC CHERAMOTI Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E.Dte.(Phase-I) | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000030/2024-2025 | 1690/RD/PHE | 10/06/2024 | 07/03/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.23 | 0 | 0 | 95
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of CHERAMOTI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001054/2022-2023 | 255/MLMD | 24/02/2023 | 25/05/2023 | DEY ENTERPRISE.. | 10.92 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of CHERAMOTI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001055/2022-2023 | 256/MLMD | 24/02/2023 | 25/05/2023 | SUDIP DEY | 10.85 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Construction of OHR & other allied works of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000316/2022-2023 | 588/RD/PHE | 24/02/2023 | 01/01/2026 | UTTAM SAHA | 128.61 | 0 | 0 | 70
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHERAMOTI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000459/2023-2024 | 567/RD/PHE | 05/03/2024 | 28/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0 | 95
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Additional Pipe Line for Providing FHTC Cheramoti Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000123/2024-2025 | 3013/RD/PHE | 03/10/2024 | 01/04/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.22 | 0 | 0 | 30
14 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Trial Run For Cheramoti PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000696/2024-2025 | 537/RD/PHE | 12/02/2025 | 13/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 | New | Making compound lighting arrangement with allied works at T/W no. I of Cheramati Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011704) | Assistant Engineer - I | Junior Engineer-07 | ORD/000711/2023-2024 | 02241/MLMD | 18/07/2023 | 15/03/2025 | ANIMA ENTERPRISE | 3.53 | 0 | 0 | 100
Total | [13 empty] | 395.64 | 0 | 0