## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 2122/RD/PHE | 03/12/2022 | 03/12/2022 | Resource Division | 69.45 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Laying Pipe line at MOKDOMPUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000037/2023-2024 | 1536/RD/PHE | 24/05/2023 | 01/04/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 65.55 | 47.48 | 72.44 | 50
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Making compound lighting arrangement with allied works at T/W no. I of Makdampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011908) | Assistant Engineer - I | Junior Engineer-07 | ORD/000708/2023-2024 | 2238/MLMD | 18/07/2023 | 16/10/2023 | J.K. ENGINEERING CO. | 3.82 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Makdampur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001881/2023-2024 | 4003133026 | 16/04/2023 | 15/07/2023 | W.B.S.E.D.C.LTD | 0.56 | 0.56 | 100 | 100
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.II of Makdampur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001882/2023-2024 | 4003133037 | 16/04/2023 | 15/07/2023 | W.B.S.E.D.C.LTD | 0.45 | 0.45 | 100 | 100
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MAKDAMPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000217/2023-2024 | 2201/MLMD | 18/07/2023 | 03/07/2025 | NEOGI ENTERPRISE. | 10.81 | 9.06 | 83.8 | 83
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Construction of Pump House & Boundary Wall at Makdampur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubaeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000258/2022-2023 | 384/RD/PHE | 08/02/2023 | 28/04/2025 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 36.14 | 22.05 | 61.02 | 60
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur -Bhatol Road due to pipe laying under Makdampur Pipe Water Supply Scheme at different stretches of road under Uttar Dinajpur Highway Division. |  |  | BILL/00320/2024-2025 | BP-2024-25-197 | 20/09/2024 | 20/09/2024 | EXECUTIVE ENGINEER PWD ROADS | 13.36 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Implementation of MAKDAMPUR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000153/2022-2023 | 1992/RD/PHE | 14/11/2022 | 03/01/2026 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 412.01 | 214.08 | 51.96 | 70
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Makdampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000441/2024-2025 | 3753/RD/PHED | 18/12/2024 | 31/07/2025 | SANDIP SARKAR | 34.56 | 0 | 0 | 65
11 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MAKDAMPUR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011908) | Assistant Engineer - I | Junior Engineer-07 | ORD/000218/2023-2024 | 2202/MLMD | 18/07/2023 | 21/05/2025 | M/S D.G.B. ENTERPRISE. | 10.92 | 9.17 | 83.97 | 100
Total | [13 empty] | 657.63 | 302.85 | 46.05