## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 574/RD/PHE | 23/02/2023 | 23/02/2023 | Resource Division | 31.27 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03539/2023-2024 | BP-2023-24-566 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03538/2023-2024 | BP-2023-24-565 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Additional Quotation for TW-II of Laksmania Water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/02075/2024-2025 | BP-2024-25-488 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 0.23 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Implementation of Laksmania and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000031/2023-2024 | 1306/RD/PHE | 12/05/2023 | 01/01/2026 | UNIVERSAL ENTERPRISES | 279.7 | 0 | 0 | 70
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Making compound lighting arrangement with allied works at T/W no. I of Laksmania Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000714/2023-2024 | 2231/MLMD | 18/07/2023 | 05/10/2025 | M/S PARIMAL DAS. | 3.83 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAKSMANIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000464/2023-2024 | 572/RD/PHE | 05/03/2024 | 30/03/2025 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 0 | 85
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd Tubewell Site and road restoration of Laksmania PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000408/2025-2026 | 1606/RD/PHE | 17/06/2025 | 15/10/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 39.5 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-07 | ORD/000213/2023-2024 | 2197/MLMD | 18/07/2023 | 22/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 11.3 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-07 | ORD/000214/2023-2024 | 2198/MLMD | 18/07/2023 | 01/03/2025 | HANNAN BUILDERS PVT. LTD. | 11.3 | 0 | 0 | 100
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0 | 0 | 100
Total | [13 empty] | 405.9 | 0 | 0